## New Street Works Report (Baker
site_name | works_location | work_start_date | work_est_end_date | org_a_group_name | contact_name | contact_phone | works_ref | works_desc
HAREWOOD AVENUE | [ttro] (Footway, Carriageway)NB/SB between Jnc Harewood Row and Marylebone Road | 2026-04-23 07:00 | 2026-06-06 | TRANSPORT FOR LONDON | Unknown | Unknown | 15265421 | Safer junction upgrades
BAKER STREET | (Footway)Outside 60 | 2026-06-05 20:00 | 2026-06-06 | TRANSPORT FOR LONDON | Lee Henley | 07827 363 064 | GB-COW-MU-00033-1 | Removal of existing telephone kiosk and reinstatement to match the surrounding materials.
GLENTWORTH STREET | (Footway)OUTSIDE 85 TO 105 | 2026-06-08 | 2026-06-09 | Thames Water Utilities Ltd | Metering - Vennsys | 07747 644653 | BULK-0357729 | BULK METER INSTALL IN THE FOOTWAY. . Footway closure: Pedestrian walkway will be provided
JAMES STREET | (Footway)Opposite 14 and 20 | 2026-06-08 | 2026-06-10 | VIRGIN MEDIA | Virgin Media - Kelly Communication | 02476 642818 | DIS172045-1 | Clear 2x Blockages on footway. . Footway closure: Alternative route will be provided
JAMES STREET | (Footway)opposite Side of Pandora Oxford Street on James Street | 2026-06-08 | 2026-06-10 | VIRGIN MEDIA | Virgin Media - Kelly Communication | 02476 642818 | DIS172045 | Clear 2x Blockage on footway. . Footway closure: Alternative route will be provided
BAKER STREET | (footway)outside 38-44 Baker St, London W1U 7AJ | 2026-06-08 | 2026-06-10 | Vorboss | Unknown | Unknown | VORDUCT660 | To supply and lay approx. 2m of 2W 96mm from existing BT chamber to communal chamber
BAKER STREET | (footway)outside 54-60 Baker St, London W1U 7DF | 2026-06-08 | 2026-06-10 | Vorboss | Unknown | Unknown | VORDUCT659 | To supply and lay approx. 6m of 2W duct from existing BT chamber to communal chamber for new service connection
LISSON GROVE | (Carriageway)01/139 Yun244518 Lisson Grove Westminster. by Harewood Row | 2026-06-11 10:00 | 2026-06-11 | TRANSPORT FOR LONDON | Unknown | Unknown | 00512012 | Slot cut c/w sensor loops to repair traffic signals SD4 plus feed to existing chamber (f/w 2m new duct and underkerb). Southbound c/w swapping lane 1 & 2 and f/w to chamber (ped access maintained). Ped access maintained. Van and additional equipment parked in bay
WIGMORE STREET | (footway)O/S 95 | 2026-06-11 20:00 | 2026-06-11 | TRANSPORT FOR LONDON | Luke Tearall | 0208 561 4959 | -BP6665 | Replacement of old bus stop pole and foundation with new. TfL stop ref [BP6665 and 5099709]
WIGMORE STREET | (footway)O/S110-116 | 2026-06-11 20:00 | 2026-06-11 | TRANSPORT FOR LONDON | Luke Tearall | 0208 561 4959 | -BP6664 | Replacement of old bus stop pole and foundation with new. TfL stop ref [BP6664 and 5099708]
ROBERT ADAM STREET | (Footway)opp. 34 - W1 | 2026-05-11 08:19 | 2026-06-12 | UK POWER NETWORKS EASTERN & LONDON | London Power Networks plc | 0800 0280709 | 04299262 | Footway closure: Pedestrian walkway will be provided
BAKER STREET | (Footway)o/s 8 - W1 | 2026-05-11 08:20 | 2026-06-12 | UK POWER NETWORKS EASTERN & LONDON | London Power Networks plc | 0800 0280709 | 74192841 | Network Operations Distribution: Install / Replace / Remove electrical link box: Approx. 6m excavation required to allow for removal of aged linkbox and provide room for siting/jointing of new box and cables
CHILTERN STREET | (Carriageway)From J/W Paddington Street - 20m South of Junction | 2026-05-28 08:00 | 2026-06-12 | City of Westminster | FMConway Permitting - Planned Works | 01732 600 771 | 06291201 | Additional Trial Holes forchange in design scope. . Footway closure: Pedestrian walkway will be provided
PADDINGTON STREET | (Carriageway)J/W Baker Street - J/W Chiltern Street | 2026-05-28 08:00 | 2026-06-12 | City of Westminster | FMConway Permitting - Planned Works | 01732 600 771 | 23465917 | Additional Trial Holes forchange in design scope. . Footway closure: Pedestrian walkway will be provided
GLENTWORTH STREET | (Footway)OUTSIDE 127-147 | 2026-06-10 | 2026-06-12 | Thames Water Utilities Ltd | Metering - Vennsys | 07747 644653 | BULK-0357749 | BULK METER INSTALL IN THE FOOTWAY. . Footway closure: Pedestrian walkway will be provided
DUKE STREET | (Footway)O/S 27 | 2026-06-10 | 2026-06-12 | BT | KNNS - Other | 01313 457381 | -MDUL-V9090 | install 2m track in FW outside 27. . Footway closure: Alternative route will be provided
GEORGE STREET | (carriageway)161-169 George Street (opp to Forset St) | 2026-06-05 08:00 | 2026-06-18 | City of Westminster | FMConway Permitting - Planned Works | 01732 600 771 | 04615612 | Cycle Improvements (Deep Drainage Connection 1). . Footway closure: Alternative route will be provided
MONTAGU MEWS SOUTH | (carriageway)Junction with George Street | 2026-06-05 08:00 | 2026-06-18 | City of Westminster | FMConway Permitting - Planned Works | 01732 600 771 | 57104782 | Cycle Improvements. . Footway closure: Alternative route will be provided
PORTMAN SQUARE | (footway, carriageway)O/S 35-38 to 40 | 2026-06-15 | 2026-06-18 | Zayo Group UK Ltd (formerly AboveNet) | AboveNet (JSM Constructions Ltd) | 01992 788019 | 26-06-001 | Customer Connection in the CW & FW
BAKER STREET | (footway)O.S Prop No's 70 - 44, W1 | 2026-06-08 08:00 | 2026-06-19 | UK POWER NETWORKS EASTERN & LONDON | London Power Networks plc | 0800 0280709 | 89290625 | Connections Projects: Disconnection / reconnection of existing electricity supply for a customer: Excavation of joint holes and track work for disconnection of an old service connection. All our works are within the site Herras Fencing.
BLANDFORD STREET | (footway)O.S No 64 -66, W1 | 2026-06-08 08:00 | 2026-06-19 | UK POWER NETWORKS EASTERN & LONDON | London Power Networks plc | 0800 0280709 | 21450413 | Connections Projects: Disconnection / reconnection of existing electricity supply for a customer: Excavation of joint holes and track work for disconnection of an old service connection. All our works are within the site Herras Fencing.
DORSET STREET | (footway)S/O No 70 & O/S 43-45, W1 | 2026-06-08 08:00 | 2026-06-19 | UK POWER NETWORKS EASTERN & LONDON | London Power Networks plc | 0800 0280709 | 87571997 | Connections Projects: Disconnection / reconnection of existing electricity supply for a customer: Excavation of joint holes and track work for disconnection of an old service connection. All our works are within the site Herras Fencing.
DUKE STREET | (footway, carriageway)os 78-75 | 2026-06-13 08:00 | 2026-06-19 | UK POWER NETWORKS EASTERN & LONDON | London Power Networks plc | 0800 0280709 | 31030797 | Connections (Major conn.): Installation of a new electricity supply for a customer: Parking/Loading Bay Suspension: Excavation for UKPN HV cable installation
WYNDHAM STREET | (footway, carriageway)Outside 31 Wyndham street | 2026-06-15 | 2026-06-19 | Thames Water Utilities Ltd | Natalie Drew | 07762 561848 | LPR-CD-WEST-004 | Works to replace lead from water main to boundary, following residents’ internal works. . Footway closure: Alternative route will be provided
BERKELEY MEWS | (Carriageway)CARRIAGEWAY OUTSIDE NO.1 | 2026-06-15 | 2026-06-19 | Cadent Gas Limited | Unknown | Unknown | 1001517020 | DISCONNECT 2 X 1 INCH SERVICES FROM MAIN IN NEARSIDE CARRIAGEWAY
KNOX STREET | (Footway)S6 - JW York Street, side of Bryanston Mansions | 2026-06-15 08:00 | 2026-06-19 | City of Westminster | FM Conway Permitting - Planned | 020 8636 8822 | 58949813 | Excavating to replace Informational Wide base posts
PORTMAN SQUARE | (Footway)S3 - outside Orchard Court | 2026-06-15 08:00 | 2026-06-19 | City of Westminster | FM Conway Permitting - Planned | 020 8636 8822 | 26949798 | Excavating to replace Informational Wide base posts
YORK STREET | (carriageway)junction with Harcourt Street | 2026-06-18 22:00 | 2026-06-19 | Vodafone | Vodafone (Ex CW - Fibre Wave Installations Ltd) | 07476 236350 | FWI4127-SPLA | TO ACCESS CHAMBER, SPLICE CABLE AND TEST OUTSGE FOR A NEW CUSTOMER SERVICE ON BEHALF OF VODAFONE
LISSON GROVE | (carriageway)Opp 1-84 Chequers House Lisson Grove, NW8 8HZ | 2026-06-19 | 2026-06-19 | Thames Water Utilities Ltd | Clean R&M - London - Winter Event | 01189340104 | 00520328 | renew frame and cover
ORCHARD STREET | [ttro] (Carriageway)Orchard street Jnc with Oxford Street London. | 2026-06-01 22:00 | 2026-06-20 | BT | Unknown | Unknown | -MH-WDPLC19Z-ORCHAR | refurb and re-roof manhole due to serious safety concern
BAKER STREET | (Carriageway)Outside 91 | 2026-06-18 | 2026-06-22 | VIRGIN MEDIA | Virgin Media - Kelly Communication | 02476 642818 | DIS172111 | Desilt Carriageway Chamber
JAMES STREET | [ttro] (Carriageway)PICTON PLACE TO BARRETT STREET | 2026-06-22 08:00 | 2026-06-22 | City of Westminster | FMConway Permitting - Planned Works | 01732 600 771 | 58744612 | Reactive carriageway repairs - S/l hra 4.5x2 1x.8 1.2x.8 1.2x1 4 areas repaint yellow lines 4.4mx50mm
HAREWOOD AVENUE | (Carriageway)o/s Waterdale Manor House, 20 Harewood Avenue, London, NW1 6AA | 2026-06-23 12:30 | 2026-06-23 | Thames Water Utilities Ltd | District Metering Maintenance | 0203 577 8114 | HFR064-3 | Sahara survey for Leak detection.
BAKER STREET | (Footway)FOOTWAY OUTSIDE NO.44,ACCURIST HOUSE | 2026-06-16 | 2026-06-24 | Cadent Gas Limited | Unknown | Unknown | 1001517854 | DISCONNECT 1 X 63MM PE SERVICE FROM MAIN IN NEARSIDE FOOTWAY FOR DEMOLITION PROJECT,WORKING UNDER CUSTOMERS HOARDING, MULTIPLE DISC ONNECTIONS TAKING PLACE ON BAKER STREET AND SURROUNDING AREAS FOR DEMOLITION PROJECT
BAKER STREET | (Footway)FOOTWAY OUTSIDE NO.62-64 | 2026-06-16 | 2026-06-24 | Cadent Gas Limited | Unknown | Unknown | 1001517855 | DISCONNECT 3 X 63MM PE SERVICE FROM MAIN IN NEARSIDE FOOTWAY FOR DEMOLITION PROJECT,WORKING UNDER CUSTOMERS HOARDING, MULTIPLE DISC ONNECTIONS TAKING PLACE ON BAKER STREET AND SURROUNDING AREAS FOR DEMOLITION PROJECT
BLANDFORD STREET | (Footway, Carriageway)FOOTWAY SIDE OF NO.38-42 BAKER STREET | 2026-06-16 | 2026-06-24 | Cadent Gas Limited | Unknown | Unknown | 1001518144 | DISCONNECT 1 X 63MM PE SERVICE FROM MAIN IN NEARSIDE FOOTWAY. . Footway closure: Alternative route will be provided
BROADSTONE PLACE | (Footway)FOOTWAY REAR OF ACCURIST HOUSE, 44 BAKER STREET | 2026-06-16 | 2026-06-24 | Cadent Gas Limited | Unknown | Unknown | 1001518170 | DISCONNECT 1 X 63MM PE SERVICE FROM MAIN IN NEARSIDE FOOTWAY. . Footway closure: Alternative route will be provided
DORSET STREET | (Footway)FOOTWAY OUTSIDE NO.43 | 2026-06-16 | 2026-06-24 | Cadent Gas Limited | Unknown | Unknown | 1001517762 | DISCONNECT 1 X 63MM PE SERVICE FROM MAIN IN NEARSIDE FOOTWAY
CHILTERN STREET | (Footway)Howarth of London 37 Chiltern Street W1U 7PW | 2026-06-18 08:00 | 2026-06-24 | UK POWER NETWORKS EASTERN & LONDON | London Power Networks plc | 0800 0280709 | 28400613 | Connections Small Service: Installation of a new electricity supply for a customer: Parking/Loading Bay Suspension: Excavation of the footway o/s No. 37 to install a new electricity service on their behalf. 4 bays to be suspended o/s for parking, spoil, and a temporary walkway to maintain pedestrian access around our works.. . Footway closure: Pedestrian walkway will be provided
LISSON GROVE | (Carriageway)OUTSIDE EARL HOUSE | 2026-06-22 | 2026-06-24 | Thames Water Utilities Ltd | Metering - Vennsys | 07747 644653 | BULK-0352282 | BULK METER INSTALLATION IN THE CARRIAGEWAY
BICKENHALL STREET | (Carriageway)O/S 159 - 236 BICKENHALL MANSIONS | 2026-06-23 | 2026-06-25 | Thames Water Utilities Ltd | Metering - Vennsys | 07747 644653 | BULK-0362623 | BULK METER EXCHANGE IN THE CARRIAGEWAY
MONTAGU MANSIONS | (Carriageway)OUTSIDE 47 TO 64 | 2026-06-23 | 2026-06-25 | Thames Water Utilities Ltd | Metering - Vennsys | 07747 644653 | BULK-0353110 | BULK METER INSTALLATION IN THE CARRIAGEWAY
OLD QUEBEC STREET | (footway)SO 508 to 540 Oxford Street in Old Quebec Street | 2026-06-24 | 2026-06-25 | Thames Water Utilities Ltd | Meter Reading - South London | 0208 2138166 | NLS00081318945-0170 | REMEDIAL WORKS IN FOOTWAY. . Footway closure: Alternative route will be provided
GLOUCESTER PLACE | [ttro] (Carriageway)O/S Number 70-68 | 2026-06-25 08:00 | 2026-06-25 | Vodafone | Jenny Robinson | 0333 304 0762 | OCU/DEF0528 | Replace CW2 Frame and Cover under S81 On Behalf of Vodafone Ltd
HAREWOOD AVENUE | [ttro] (Footway)Between Melcombe Pl and Marylebone Rd | 2026-05-20 08:00 | 2026-06-27 | City of Westminster | FMConway Permitting - Planned Works | 01732 600 771 | 87704936 | Footway repaving and installation of cycleway segregation kerb. . Footway closure: Alternative route will be provided
DUKE STREET | (Carriageway)from J/o Brown Hat Gardens (South) to j/o Brown Hart Gardens (north) | 2026-06-17 08:00 | 2026-07-02 | UK POWER NETWORKS EASTERN & LONDON | London Power Networks plc | 0800 0280709 | 55437687 | Connections (Major conn.): Installation of a new electricity supply for a customer: Parking/Loading Bay Suspension: Excavation for UKPN HV cable installation
MANCHESTER STREET | (Footway)Outside 27 Manchester Street, London, W1U 4DJ | 2026-06-30 | 2026-07-04 | Cadent Gas Limited | Unknown | Unknown | 1001517296 | SERVICE RELAY DUE TO CORRODED SUPPLY TO PROPERTY
HAREWOOD AVENUE | (carriageway)From J/W Rossmore Road - J/W Broadley Terrace | 2026-06-25 08:00 | 2026-07-10 | City of Westminster | FMConway Permitting - Planned Works | 01732 600 771 | 51548637 | Trial holes for the implementation of a cycle scheme
SEYMOUR STREET | (Footway)O/S. 12-18- W1H | 2026-07-06 08:00 | 2026-07-10 | UK POWER NETWORKS EASTERN & LONDON | London Power Networks plc | 0800 0280709 | 49679636 | Connections Projects: Installation of a new electricity supply for a customer: Parking/Loading Bay Suspension: Excavation of joint holes to install a 100A BNO and disconnection of an old service connection.. . Footway closure: Pedestrian walkway will be provided
FITZHARDINGE STREET | [ttro] (Carriageway)From junction of Baker St to junction of Manchester Sq | 2026-06-22 08:00 | 2026-07-16 | UK POWER NETWORKS EASTERN & LONDON | London Power Networks plc | 0800 0280709 | 10491945 | Connections (Major conn.): Installation of a new electricity supply for a customer: Parking/Loading Bay Suspension: Excavation for UKPN HV cable duct installation
PORTMAN SQUARE | [ttro] (Carriageway)Portman Square/J/W Gloucester Place | 2026-07-20 08:00 | 2026-07-20 | City of Westminster | FMConway Permitting - Planned Works | 01732 600 771 | 10871595 | Reactive Carriageway repairs - S/l hra 10mx.3m then s/l buff anti skid 10mx.3m
HAREWOOD AVENUE | (carriageway)Junction with Rossmore Road and Broadley Terrace | 2026-07-13 08:00 | 2026-07-24 | City of Westminster | FMConway Permitting - Planned Works | 01732 600 771 | 01497406 | Trial holes for the implementation of a cycle scheme
BAKER STREET | (Carriageway)at the junction of Fitzhardinge Street/Portman Sq | 2026-07-17 08:00 | 2026-07-28 | UK POWER NETWORKS EASTERN & LONDON | London Power Networks plc | 0800 0280709 | 24155081 | Connections (Major conn.): Installation of a new electricity supply for a customer: Parking/Loading Bay Suspension: Excavation for new UKPN HV cable installation
GEORGE STREET | [ttro] (Carriageway)Edgware Road to Gloucester Place | 2026-01-23 08:00 | 2026-08-03 | City of Westminster | FMConway Permitting - Planned Works | 01732 600 771 | 57146012 | Cycle Improvements. . Footway closure: Alternative route will be provided
LUXBOROUGH STREET | (carriageway)O/s 20 Luxborough Street East Marylebone Marylebone City of Westminster England W1U 5BS. WORK IS ON CARRIAGEWAY. | 2026-08-04 21:00 | 2026-08-05 | BT | Unknown | Unknown | WH2CG82DSB | 3 WAY LIGHTS IS REQUIRED FOR SAFE ACCESS TO JOINT BOX FOR CABLING WORK.
BAKER STREET | (Footway, Carriageway)Outside No. 20 | 2026-08-06 20:00 | 2026-08-07 | Vodafone | Vodafone (Ex CW - Fibre Wave Installations Ltd) | 07476 236350 | FWI3949-SPL | Splicing/ Cabling on behalf of Vodafone. In conjunction with NX508FWI3949-SPL-S1B
BAKER STREET | (Footway, Carriageway)Outside No. 38 to No. 44 | 2026-08-06 20:00 | 2026-08-07 | Vodafone | Vodafone (Ex CW - Fibre Wave Installations Ltd) | 07476 236350 | FWI3949-SPL-S1B | Splicing/Cabling on behalf of Vodafone. inconjunction with NX508FWI3949-SPL
ALLSOP PLACE | [ttro] (Footway, Carriageway)O.S 4 to 63 Farley Court & O.S Stardome, NW1 | 2026-08-03 08:00 | 2026-08-14 | UK POWER NETWORKS EASTERN & LONDON | London Power Networks plc | 0800 0280709 | 54899895 | Connections Projects: Installation of a new electricity supply for a customer: Excavation to divert and lower an LV cable so that Conway can install bollards. Directional road closure.. . Footway closure: Alternative route will be provided
UPPER BERKELEY STREET | [ttro] (Carriageway)o/s no 27 | 2026-08-10 | 2026-08-14 | Thames Water Utilities Ltd | Meter Reading - South London | 0208 2138166 | NLS00081400259-045 | NLS - NEW WATER CONNECTION - Plot 1: 1x50mm MDPE Non-revenue Dedicated Fire Supply Connection off: 5" CI Offsite
LISSON GROVE | [ttro] (Carriageway)J/W Broadley Street | 2026-07-31 08:00 | 2026-08-18 | City of Westminster | FMConway Permitting - Planned Works | 01732 600 771 | 54411739 | Trial holes for the implementation of a cycle scheme
BAKER STREET | [ttro] (Carriageway)O/s 70 to 20 | 2026-08-17 20:00 | 2026-08-18 | CenturyLink Communications UK Limited | GLOBAL CROSSING | 020 8731 4600 | CABLING-006880 | Cabling Works
DUKE STREET | [ttro] (Carriageway)from junction of Brown Hart Gardens (north) (PH5-6) to junction of Wigmore Street | 2026-07-03 08:00 | 2026-08-26 | UK POWER NETWORKS EASTERN & LONDON | London Power Networks plc | 0800 0280709 | 17595539 | Connections (Major conn.): Installation of a new electricity supply for a customer: Excavation to install new UKPN HV cables
KENRICK PLACE | (Carriageway)J/W Paddington Street | 2026-06-15 08:00 | 2026-09-01 | City of Westminster | FMConway Permitting - Planned Works | 01732 600 771 | 55994981 | Stage 5 Construction. . Footway closure: Pedestrian walkway will be provided
SHERLOCK MEWS | [ttro] (Carriageway)J/W Paddington Street | 2026-06-15 08:00 | 2026-09-01 | City of Westminster | FMConway Permitting - Planned Works | 01732 600 771 | 51588554 | Stage 5 Construction. . Footway closure: Pedestrian walkway will be provided
GEORGE STREET | [ttro] (Carriageway)Edgware Road to Gloucester Place | 2026-08-28 08:00 | 2026-09-04 | City of Westminster | FMConway Permitting - Planned Works | 01732 600 771 | 09678762 | Resurfacing. . Footway closure: Alternative route will be provided
CHILTERN STREET | [ttro] (Footway, Carriageway)O/S 74 - 84 WENDOVER COURT | 2026-09-01 | 2026-09-08 | Thames Water Utilities Ltd | Meter Reading - South London | 0208 2138166 | NLS00081458686-0045 | NLS - NEW WATER CONNECTION - NHH Plot 1, 1x25mm MDPE Mtrd Supply. . Footway closure: Pedestrian walkway will be provided
CHILTERN STREET | [ttro] (Carriageway)20m from J/W Paddington Street in both directions North & South | 2026-06-15 08:00 | 2026-09-09 | City of Westminster | FMConway Permitting - Planned Works | 01732 600 771 | 08163098 | stage 5 Construction. . Footway closure: Pedestrian walkway will be provided
PADDINGTON STREET | [ttro] (Carriageway)From J/W Baker Street - J/W Ashland Place | 2026-06-15 08:00 | 2026-09-09 | City of Westminster | FMConway Permitting - Planned Works | 01732 600 771 | 91779443 | Stage 5 Construction. . Footway closure: Pedestrian walkway will be provided
BRUNSWICK MEWS | [ttro] (Carriageway)JUNCTION WITH GREAT CUMBERLAND PLACE | 2026-09-07 08:00 | 2026-09-09 | City of Westminster | FMConway Permitting - Planned Works | 01732 600 771 | 62501226 | Reactive carriageway repairs - R/L granite kerbs 4.5LM, S/L crimp rolled grano/concrete 4mx0.75m, R/L granite setts 5mx1.2m.
BLANDFORD STREET | (Footway, Carriageway)Outside and opposite the corner of 64-66 | 2026-09-07 | 2026-09-11 | VIRGIN MEDIA | Virgin Media - Kelly Communication | 02476 642818 | DIS169584-4 | 13m carriageway ducting - carriageway crossing
BLANDFORD STREET | (Footway, Carriageway)O.S No 64 - 66, W1 | 2026-09-01 08:00 | 2026-09-14 | UK POWER NETWORKS EASTERN & LONDON | London Power Networks plc | 0800 0280709 | 39608242 | Connections Projects: Installation of a new electricity supply for a customer: EXCAVATE AND EXPOSE BOTH LV CABLES IN BLANDFORD STREET. THEY WILL THEN NEED TO BE RE LOCATED INTO THE GRPS.
BROADSTONE PLACE | (Carriageway)O.S No 1 to 5, W1 | 2026-09-01 08:00 | 2026-09-14 | UK POWER NETWORKS EASTERN & LONDON | London Power Networks plc | 0800 0280709 | 13054564 | Connections Projects: Installation of a new electricity supply for a customer: Parking/Loading Bay Suspension: EXCAVATE OUTSIDE TC 36015 AND TC 34110 AND EXPOSE ALL CABLES AND FIND THE NEW BANK OF 8X DUCTS INSTALLED PREVIOUSLY. ALL OUR WORKS ARE WITHIN THE SITE HOARDING.
NEW QUEBEC STREET | [ttro] (Carriageway)at the junction of Upper Berkeley Street | 2026-10-02 08:00 | 2026-10-08 | UK POWER NETWORKS EASTERN & LONDON | London Power Networks plc | 0800 0280709 | 79804847 | Connections (Major conn.): Installation of a new electricity supply for a customer: Road closure for works on Upper Berkeley Street
GLOUCESTER PLACE | [ttro] (Carriageway)CRAWFORD STREET TO YORK STREET | 2026-10-12 08:00 | 2026-10-12 | City of Westminster | FMConway Permitting - Planned Works | 01732 600 771 | 57270991 | Reactive carriageway repairs - S/l hra 2mx1m adjust frame and cover s/l anti skid 2mx1m
BERKELEY MEWS | [ttro] (Carriageway)junction of Upper Berkeley Street | 2026-10-09 08:00 | 2026-10-17 | UK POWER NETWORKS EASTERN & LONDON | London Power Networks plc | 0800 0280709 | 68463020 | Connections (Major conn.): Installation of a new electricity supply for a customer: Road closure for works on Upper Berkeley Street
UPPER BERKELEY STREET | (Carriageway)from junction of Seymour Place to junction of Portman Square | 2026-08-24 08:00 | 2026-11-03 | UK POWER NETWORKS EASTERN & LONDON | London Power Networks plc | 0800 0280709 | 69412512 | Connections (Major conn.): Installation of a new electricity supply for a customer: Parking/Loading Bay Suspension: Excavation to install new UKPN HV cables
PORTMAN SQUARE | [ttro] (Carriageway)from Gloucester Sq to Baker St | 2026-10-30 08:00 | 2026-11-19 | UK POWER NETWORKS EASTERN & LONDON | London Power Networks plc | 0800 0280709 | 12818578 | Connections (Major conn.): Installation of a new electricity supply for a customer: Excavation for UKPN HV cable installation
SEYMOUR MEWS | [ttro] (Carriageway)junction of Fitzhardinge Street | 2026-11-27 08:00 | 2026-12-01 | UK POWER NETWORKS EASTERN & LONDON | London Power Networks plc | 0800 0280709 | 88568850 | Connections (Major conn.): Installation of a new electricity supply for a customer: Road closure for UKPN duct installation works on Fitzhardinge Street
PORTMAN SQUARE | (Footway)fw near junction Upper Berkeley Street | 2026-05-18 08:00 | 2026-12-15 | UK POWER NETWORKS EASTERN & LONDON | London Power Networks plc | 0800 0280709 | 77072967 | Connections (Major conn.): Spoil / materials / equipment only: Permit to place a welfare unit for our major project in the area
MARYLEBONE ROAD | [ttro] (Carriageway)From J/W Allsop Place - O/S Madame Tussauds (end of the red route parking bays) | 2026-05-19 07:00 | 2026-12-15 | City of Westminster | Section 50 Licences | 0207 641 3924 | 10259549 | Utility diversion, footway excavation, installation of HVM bollards, reinstate footway. . Footway closure: Pedestrian walkway will be provided
ALLSOP PLACE | [ttro] (Footway, Carriageway)From J/W Cornwall Terrace Mews - J/W Marylebone Road | 2026-05-19 07:00 | 2026-12-15 | City of Westminster | Section 50 Licences | 0207 641 3924 | 42804279 | Utility diversion, footway excavation, installation of HVM bollards, reinstate footway. . Footway closure: Pedestrian walkway will be provided
MANCHESTER SQUARE | [ttro] (Carriageway)junction of Fizthardinge Street to Duke Street | 2026-12-11 08:00 | 2026-12-17 | UK POWER NETWORKS EASTERN & LONDON | London Power Networks plc | 0800 0280709 | 06150934 | Connections (Major conn.): Installation of a new electricity supply for a customer: Excavation for UKPN HV cable ducts installation